## Logsheet
FY22/23 Research Logsheet (Carnivore 2 & 3)
Date | Time | Name(s) | Tasks | Remarks
09/05/2022 | 1455 - 1600 | Daniel | Planning | Finalising Methodology; Intern's workflow; Confirming meeting date
10/05/2022 | 1600 - 1700 | Daniel; Krys | Planning | Setting up Zoomonitor project and trialing user interface
11/05/2022 | 1300 - 1430 | Daniel; Krys | Trial Study (Dholes) | Conducted Dhole trial study; trialled different scents (blood, banana, coffee); Trialled usage of zoomonitor for data collection
11/05/2022 | 1300 - 1430 | Yuting; Shaikh | Trial Study (Dholes) | Assisting with, spraying of scents, confining and releasing animals; assisted to collect coffee grinds for scent
12/05/2022 | 1600 - 1730 | Daniel | Planning | Townhall meeting attended concurrently; Adjustments to methodology; adjustments to Dhole zoomonitor project file; setting up Tiger zoomonitor project file
14/05/2022 | 1600 - 1700 | Daniel; Krys | Trial Study (Tigers) | Conducted Tiger trial study; trialled usage of blood; adjustments to Zoo Monitor file
18/05/2022 | 1600 - 1815 | Daniel; Krys | Meeting | Meeting to finalise intern's workflow and study methodology
20/05/2022 | 1600 - 1700 | Daniel | Planning | Updating CSMC on Intern's workflow; liasing with Halim to collect samba deer fecal
24/05/2022 | 1300 - 1430 | Daniel | Introduction & Orientation | Orientation for the intern; explanantion of intern's deliverables, study methodology and workflow
26/05/2022 | 1300 - 1515 | Daniel; Krys | Pilot study (Dholes) | Conducted first pilot study for Dholes; adjustments to Dhole Zoomonitor project file
27/05/2022 | 1300 - 1545 | Daniel; Krys | Pilot study (Tigers) | Conducted first pilot study for Tiger; adjustments to Tiger Zoomonitor
28/05/2022 | 1600 - 1730 | Daniel; Krys | Planning | Creating randomised schedule for location that are to be scented; finding references for ethogram behaviour descriptions
31/05/2022 | 1345 - 1630 | Krys; Riana | Pilot study (Dholes and Tigers) | Pilot study for both Dholes and Tiger. Helped to confine and release animal, spraying of scent on locations
2022-06-06 | 1330 - 1530 | Daniel; Amanda; Sandra; Celeste | RFN Study | RFN study for both species.
16/6/2022 | 1300 - 1400 | Daniel; Ewen; Goon yin | RFN Study (Dholes)
16/6/22 | 1400 - 1500 | Daniel; Sandra; Celeste | RFN Study (Tiger)
17/6/22 | 1330 - 1530 | Riana; Daniel; Celeste; Amanda; Goon yin | RFN Study (Dholes & Tiger)
18/6/22 | 1330 - 1430 | Yuting; Daniel; Krys | RFN Study (Dholes)
18/6/22 | 1430 - 1530 | Muzafar; Daniel; Krys | RFN Study (Tiger)
20/6/22 | 1330 - 1430 | Krys; Ewen; Vernice | RFN Study (Dholes)
20/6/22 | 1430 - 1530 | Krys; Riana; Sandra | RFN Study (Tiger)
21/6/22 | 1330 - 1530 | Daniel; Charmaine; Amanda; Celeste | RFN Study (Dholes & Tiger)
22/6/22 | 1330 - 1430 | Daniel; Julette; Vernice | RFN Study (Dholes)
22/6/22 | 1430 - 1530 | Daniel; Amanda; Sandra; Celeste | RFN Study (Tiger)